## 🗺️ Sample Student Director Road Map

Program Year: September 1 – April 1
 Total Target Hours: ~200 hours
 (Average: ~25 hours/month)

### ✅ September (25–30 hrs)

- Complete Orientation Training (Brightspace modules) – 3 hrs

- Meet with Supervisor to finalize goals, expectations, and road map – 1.5 hrs

- Participate in First2 Statewide Kickoff Meeting (if scheduled) – 2 hrs

- Plan and lead or support a welcome/STEM event on campus – 5–7 hrs

- Outreach to new students: tabling, emails, class visits – 4–5 hrs

- Start a Slack channel or small group for campus communications – 1.5 hrs

- Join weekly or biweekly campus team meetings (1–2) – 2 hrs

- Weekly Slack check-ins, journal entries, and planning – 3–4 hrs

- Coordinate carpooling or travel for off-campus First2 events (if applicable) – 2 hrs

### ✅ October (25–30 hrs)

- Regular Supervision Meetings (2–4x) – 3–4 hrs

- Facilitate or lead one improvement project (e.g., study group, student panel) – 5–6 hrs

- Peer mentoring or student check-ins (weekly) – 4–5 hrs

- Participate in institutional change team activities – 3 hrs

- Prepare and submit progress report with reflections – 1.5 hrs

- Attend statewide training or workshop – 2 hrs

- Slack posts and group coordination – 2–3 hrs

- Assist with First2 student recruitment or retention efforts – 3 hrs

### ✅ November (22–28 hrs)

- Supervision Meetings (2x) – 2 hrs

- Continue mentoring or peer leadership efforts – 4–6 hrs

- Organize or support mid-semester student feedback session – 2–3 hrs

- Implement a data-related activity or help analyze feedback – 3 hrs

- Slack group engagement and planning – 2–3 hrs

- Support a fall outreach or community-based STEM activity – 4–5 hrs

- Prepare for First2 Fall meeting or session – 3 hrs

- Write or record a mid-semester reflection/story for First2 site – 1–2 hrs

### ✅ December (15–20 hrs)

- Supervision Meeting (1x) – 1 hr

- Wrap-up peer group or improvement activity – 3–4 hrs

- Slack reflection post or end-of-term check-in with student team – 2 hrs

- Submit semester report + hours log – 2 hrs

- Help plan or contribute to early spring planning discussions – 2–3 hrs

- Optional statewide call or small group reflection – 2 hrs

- Time bank for supporting special projects or event planning – 3–5 hrs

### ✅ January (25–30 hrs)

- Re-orientation with Supervisor or team – 2 hrs

- Launch a spring engagement initiative (e.g., peer mentoring, affinity group) – 6–8 hrs

- Host a STEM reentry or goal-setting session for students – 3 hrs

- Join statewide First2 meeting or student director training – 2 hrs

- Ongoing peer mentoring or group facilitation – 4–5 hrs

- Slack and email coordination for spring efforts – 3 hrs

- Reflection post + hours update – 1 hr

- Support spring student recruitment or retention – 3–5 hrs

### ✅ February (25–30 hrs)

- Regular Supervision Meetings (2x) – 2 hrs

- Lead or contribute to campus improvement or research-informed project – 6–8 hrs

- Mentoring or community-building (weekly) – 5–6 hrs

- Write a short impact story or record a video update – 2 hrs

- Contribute to data gathering, analysis, or student-led surveys – 3 hrs

- Plan or help coordinate spring First2 campus event – 4–6 hrs

- Slack engagement and mid-semester coordination – 3 hrs

- Reflection journal/check-in – 1 hr

### ✅ March (25–30 hrs)

- Regular Supervision Meetings (2x) – 2 hrs

- Prepare for and present at spring First2 event or statewide share-out – 5–6 hrs

- Document and share project outcomes, reflections, or process map – 3–4 hrs

- Complete or help wrap up spring improvement initiatives – 4–6 hrs

- Continue peer leadership and mentoring work – 4 hrs

- Slack communication and celebration planning – 2 hrs

- Plan for end-of-year transitions, documentation, or training incoming leaders – 3–4 hrs

### ✅ April 1 Wrap-Up (5–7 hrs)

- Final reflection and hours report submission – 2 hrs

- Participate in debrief or celebration meeting – 1–2 hrs

- Complete peer thank-yous, transitions, or support recruitment for summer – 2–3 hrs

### 🧮 Total Estimated Hours: 202–206 hrs